## Sheet1
Version	Issue/Improvement Idea	Plan to Resolve?	Resolved in Working Files?

V0.2.0 Beta	Whitecloaks have bad face keys	Yes	Yes
V0.2.0 Beta	Magic Effect Error (sounds but no visuals)	Not sure it exists	???
V0.2.0 Beta	Can't zoom on towns near the edge of the map	???	No
V0.2.0 Beta	Scenes don't match environment of surrounding map area	Yes	Yes
V0.2.0 Beta	No Campaign	???	No
V0.2.0 Beta	Quick battle trolloc character needs to be a trolloc type	Yes	Yes
V0.2.0 Beta	Remove burn over time exp over time	Yes	Yes
V0.2.0 Beta	Look more into the 'airborne' code, it seems to have problems, remove effect for NPCs	Yes	Yes
V0.2.0 Beta	Add more troops types for quick/custom battle	Yes	Yes
V0.2.0 Beta	Add Steddings	???	???
V0.2.0 Beta	Power weapons / angreal, ter'angreal	???	???
V0.2.0 Beta	LOD models for dresses and shadowspawn heads	Yes	No
V0.2.0 Beta	Remove non-ranged One Power Items from computer troops.	Yes	Yes
V0.2.0 Beta	Make it so 'Player' cannot be affected by compulsion	Yes	Yes
V0.2.0 Beta	Aes Sedai follow Warder error	Yes	Yes
V0.2.0 Beta	Lords who don't have indoor armor are naked.	???	???
V0.2.0 Beta	Shadowspawn at peace in the beginning, so they don't get wiped out	???	???
V0.2.0 Beta	Make a note to turn off damage reporting.	Yes	Yes
V0.2.0 Beta	Random player getting knocked out in sieges. When chain casting.	???	???
V0.2.0 Beta	Nerf the damage done by earth blast. In sieges, since no sliding, can kill massive number of enemies	???	No	fixed in 0.2.3
V0.2.0 Beta	Can balefire yourself and your horse	???	???
V0.2.0 Beta	Spawned agents that come with horses are mounted for sieges.	Yes	Yes
V0.2.0 Beta	Aiel bandits need a foot soldier rather than a horse for their map icon.	Yes	Yes
V0.2.0 Beta	Add Recruiter Kit by hessuu	Yes	Yes

V0.2.2 Beta	If you start in Tar Valon, you will see the wrong merchant in the tavern, and the lair spawns near (player)	Yes	Yes
V0.2.2 Beta	Seeker weave not working????	Yes	Yes
V0.2.2 Beta	Multiplayer	Yes	Yes
V0.2.2 Beta	One Power weapon: needs new mesh so it doesn't look like a dagger	Yes	Yes
V0.2.2 Beta	Correct who is married to who.	Yes	No
V0.2.2 Beta	Raise channeling modifier even if weave is ineffective	Yes	Yes
V0.2.2 Beta	Make sure player gets xp if they channel a lot	Yes	Yes

V0.2.3 Beta	Fix ground level in Bandar Eban and some other town in the south.	Yes	Yes
V0.2.3 Beta	Dragonsworn bandits won't help eachother	???	???	fixed in 0.2.5
V0.2.3 Beta	Bandit lair spawns are out of control	???	???
V0.2.3 Beta	Some bandit lairs have the wrong troops	Yes	Yes
V0.2.3 Beta	Recruit from towns	Yes	Yes
V0.2.3 Beta	Recruit options for Shadowspawn (trollocs)	Yes	Yes
V0.2.3 Beta	Villages offer new faction recruits when they are conquered	Yes	Yes
V0.2.3 Beta	Troop all 'archers' need to make them infantry and cavalry where appropriate	Yes	Yes
V0.2.3 Beta	Upgrade tree for women followers, hunter of the horn, wisdom, kin, cha' faile	Yes	Yes
V0.2.3 Beta	Talk to the village elder from the village menu – credits HokieBT	Yes	Yes
V0.2.3 Beta	When recruiting, ask for the recruits of specific countries within the faction.	Yes	Yes
V0.2.3 Beta	Pay more to guarantee recruits.	Yes	Yes
V0.2.3 Beta	Lord armies and town/castle garrison more likely to be troop from home country	Yes	Yes
V0.2.3 Beta	Channeler Recruiting Option	Yes	Yes
V0.2.3 Beta	Talk to the guild master from the town menu – credits HokieBT	Yes	Yes

V0.2.4 Beta	Kinswomen can spawn warders since they have the Yellow Ajah power weapon.	Yes	Yes
V0.2.4 Beta	Add more features from Diplomacy	???	???
V0.2.4 Beta	Update Companions	Yes
V0.2.4 Beta	Add One Power weapon to be used by companions	Yes
V0.2.4 Beta	Make it so there are fewer channelers in npc armies/garrisons	Yes	Yes
V0.2.4 Beta	Make a second face code for each of the nationalities (for more variety)	???	???
V0.2.4 Beta	Prisoner release quest fails (at least in Illian)	Yes	Yes
V0.2.4 Beta	Error codes that throw when a castle/town gets taken by another faction (cf_reinforce_party)	Yes	Yes
V0.2.4 Beta	Bandit parties with 'white' names will work together, but the other ones don't	Yes	Yes
V0.2.4 Beta	Add the character creation stuff made by Lorenzogarch	Yes	Yes
V0.2.4 Beta	Adjust 'airborne' code so agents can't get pushed off the map (getting stuck out of bounds)	No	No
V0.2.4 Beta	Make it so compelled agents are killed at the end of the round (don't have to fight them again)	Yes	Yes
V0.2.4 Beta	New weaves? (lightning strike, fire/earth blast that goes forward and keeps destroying as it goes)	???	???
V0.2.4 Beta	More Intelligent npc channeling. (so they don't kill allies as much; so they can aim ranged weaves)	Yes	Yes
V0.2.4 Beta	Recruiting dialog errors when you start your own kingdom. (for channelers, trollocs, and outlanders)	Yes	Yes
V0.2.4 Beta	Fix Ashaman spawns. Fewers sisters and also include more of the Ajahs	Yes	Yes
V0.2.4 Beta	Shaido Bandits that spawn later in the western lands	Yes
V0.2.4 Beta	Ogier Steddings	Yes
V0.2.4 Beta	Waygates	Yes
V0.2.4 Beta	Tuathuan	Yes
V0.2.4 Beta	Reduce the number of Lordly warhorses	Yes	Yes
V0.2.4 Beta	No more white and brown spotted Myrddraal horses	Yes	Yes
V0.2.4 Beta	Draghkar kill your men if you're allied with Shadowspawn and help them in a battle.	Yes	Yes
V0.2.4 Beta	Made Shadowspawn armies larger.	Yes	Yes
V0.2.4 Beta	Fix other issues that may have been made by the “allies not on same 'team' “ error	Yes	Yes
V0.2.4 Beta	Toned down friendly fire a little. Allies will no longer hit eachother with weaves every time.	Yes	Yes

V0.2.5 Beta	Channeling learner messages show up even for non-channelers
V0.2.5 Beta	Non-channelers can press 'M' to get the one power item
V0.2.5 Beta	Tweak leadership to give more party size bonuses.
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta
V0.2.5 Beta